## AOC
| Last Updated | 2020-07-27 | [9 empty] | 0
ITEM REF | NON CONFORMANCE | STANDARD USED | FINDING LEVEL | FINDING ISSUED ON | FIRST COMPLIANCE DATE | SECOND COMPLIANCE DATE | DAYS TO DUE DATE | AUDITEE CLOSURE DATE | FINDING STATUS | OBJECTIVE EVIDENCE | REMARKS | KEY
FLT 09.04 | At the time of the audit, the auditee could not sufficiently demonstrate that a system is in place to monitor duty time for Operations personnel and Freelance pilots | OMA Sec 7 | MAJOR | 2020-02-27 | 2020-03-26 |  | -79 | 2020-06-13 | CLOSED | Extract from personnel time logs registered by logging system | Finding closed.Follow up to be made during the next Audit.Finding closed late
SEC 1.1.2 | There is no clear procedure for delegation of security functions, given the security manager works alone and is busy with other roles as the AM | KCARS REG 14 | MINOR | 2020-03-02 | 2020-06-01 |  | -56 |  | OPEN
SEC 1.1.4 | There are no documented personnel evacuation procedures in event of incidents that may require either partial or total evacuation/lockdown of a station. Its recommended that procedures be developed and documented, applicable to various stations and personnel briefed/trained on the same. | KCARS REG 14 | MINOR | 2020-03-02 | 2020-06-01 |  | -56 |  | OPEN
SEC 1.2 | Inadequate recurrent reminders of the security policy, responsibilities and procedures to personnel periodically. | KCARS REG 14 | MINOR | 2020-03-02 | 2020-06-01 |  | -56 |  | OPEN
SEC 1.4 | The duties of other employees apart from the security manager and departmental heads are not outlined. Its recommended that the departmental security representatives be advised on their security roles and the same be documented |  | MINOR | 2020-03-02 | 2020-06-01 |  | -56 |  | OPEN
SEC 1.6 | The auditee could not demonstrate that there is documentary evidence to support personnel background checks are done before recruitment and after every 3 years. |  | MINOR | 2020-03-02 | 2020-06-01 |  | -56 |  | OPEN
Formulas:
DAYS TO DUE DATE = DAYS([FIRST COMPLIANCE DATE],[AUDITEE CLOSURE DATE])
DAYS TO DUE DATE = DAYS([FIRST COMPLIANCE DATE],TODAY())

## AMO
| Last Updated | 2020-07-27
ITEM REF | NON CONFORMANCE | STANDARD USED | FINDING LEVEL | FINDING ISSUED ON | FIRST COMPLIANCE DATE | SECOND COMPLIANCE DATE | DAYS TO DUE DATE | AUDITEE CLOSURE DATE | FINDING STATUS | OBJECTIVE EVIDENCE | REMARKS | KEY
O2.01 | The in-stock quantity of several parts has been flagged by the system to be below the company minimum order quantity | SPM SEC 8 | MAJOR | 2020-06-08 | 2020-07-07 |  | -20 |  | OPEN |  | Finding remains open pending rollout of new stores management sysytem
O2.02(1) | Rejection on non-conforming parts/components procedure in the SPM section 5.0 not adequate to ensure a closed loop system for implementing corrective actions. For example, reporting the same to the supplier and management. | SPM SEC 9 | MAJOR | 2020-06-08 | 2020-07-07 |  | -3 | 2020-07-10 | CLOSED |  | Finding closed Satisfactorily. Finding closed late
O2.02(2) | Life Vests received on 11/05/2020 but as at 21/05/2020 the system had not been updated to reflect the receipt | SPM SEC 9 | MAJOR | 2020-06-08 | 2020-07-07 |  |  | 2020-07-06 | CLOSED | Extract from SPM documenting the timeline allowed for the records to be entered into the system | Closed satisifactorily on time
O2.03(1) | Hose pipes in the consumable stores are not labeled to specify which fluid they are used to drain to avoid contamination or mix-up. | SPM SEC 4 | MINOR | 2020-06-08 | 2020-09-07 |  |  | 2020-07-06 | CLOSED | Picture of the separated bins containing different draining pipesfor different fluids | Closed satisifactorily on time
O2.03(2) | At the time of the Audit the “goods outward “section had items not belonging to the area. | SPM SEC 4 | MINOR | 2020-06-08 | 2020-09-07 |  |  | 2020-07-06 | CLOSED | Picture of a clear goods outwards section | Closed satisifactorily on time
O2.05 | At the time of the audit, pressure gauge S/No 126001 found in the tools store, although calibrated the system had not been updated and thus was showing the gauge was due for calibration on 2/05/2020 | SPM SEC 18 | MINOR | 2020-06-08 | 2020-09-07 |  |  |  | CLOSED | Extract from SPM documenting the timeline allowed for the records to be entered into the system | Closed satisifactorily on time
O1.08 | At the time of the audit, a mouse to one of the computers was not working therefore only three computers were complete and ready for use. | .. MPM SEC 2.8 | MINOR | 2020-06-08 | 2020-09-07 |  |  | 2020-06-30 | CLOSED | Picture of the new mouse purchased and installed | Closed satisifactorily on time
O1.10 | Line station work order packs assigned to specific Engineers in the Technical records system are not updated to reflect Engineers rotation or handover. | MPM SEC 2 | MINOR | 2020-06-08 | 2020-09-07 |  |  | 2020-06-30 | CLOSED | Email evidence on the new routine to be used in managing outstation workpacks | Closed satisifactorily on time
Formulas:
DAYS TO DUE DATE = DAYS([FIRST COMPLIANCE DATE],TODAY())
DAYS TO DUE DATE = DAYS([FIRST COMPLIANCE DATE],[AUDITEE CLOSURE DATE])

## LINE STATIONS
| Last Updated | 2020-07-27 | [9 empty] | 0
KALEMIE STATION
ITEM REF | NON CONFORMANCE | STANDARD USED | FINDING LEVEL | FINDING ISSUED ON | FIRST COMPLIANCE DATE | SECOND COMPLIANCE DATE | DAYS TO DUE DATE | AUDITEE CLOSURE DATE | FINDING STATUS | OBJECTIVE EVIDENCE | REMARKS | KEY
O7.01 | -No fire extinguisher at the batteries section on the ground floor of the house while 2 fire extinguishers are on the 1st floor. -Control of first aid kit could not be demonstrated.Contents list not updated.Missing panadol,immodium,maramoja,surgical blade 1pc while list states 2pc. | Safety | Minor | 2020-03-31 | 2020-06-01 |  |  | 2020-05-18 | CLOSED | Updated first aid Kit list and fire extinguisher printout | Closed satisfactorily on time
O1.07 | No handover between Kingsley and Presley | SFOM sec 11.1 | Major | 2020-03-31 | 2020-05-04 |  |  | 2020-04-15 | CLOSED | Email extract reminding personnel of company procedures regarding handovers | Closed on time
O1.05 | New serviceable tags not available at station | MPM Part 5 | Minor | 2020-03-31 | 2020-06-01 |  |  | 2020-05-07 | CLOSED | Non given | N/A due to station closure
O1.08 | -Re-order qty used as miimus stock.Not all consumables have a re-order qty -Control of shelf-lifed items and consumables could not be demonstrated -Kolor Kut paste has no expiry or indicated shelf life -Thycol found expired DEC 2019 -Parts issued book has no column for Defect -Misuse of parts issued book with some Engineers filling one item per page | MPM SEC L2 | Minor | 2020-03-31 | 2020-06-01 |  |  | 2020-04-15 | CLOSED | Extracts from the new parts issued book Shipment document for a replacement for the expired Thyco | Closed Satisifactorily on time
O1.03 | -IPC on dropbox REV 48 while current is REV 49 -SRM on dropbox REV 11 while Current is REV 12 | MPM SEC L2 | Minor | 2020-03-31 | 2020-06-01 |  |  | 2020-05-07 | CLOSED | MPM extract and email extract | Closed Satisifactorily on time
01.02(2) | -Security policy in the AVSEC Manual not signed by AM -Security Policy in the AVSEC Manual on dropbox not signed by AM | AVSEC Manual | Minor | 2020-03-28 | 2020-06-01 |  | -56 |  | OPEN | None given | Unsatisifactory.Finding remains open
01.02(1) | Route and aerodrome Guide;Jeppessen plates expired 14.02.2020(Recommended Jeppessen app on ipda for auto-updates) | OMC | Minor | 2020-03-31 | 2020-06-01 |  |  | 2020-05-31 | CLOSED | None given | Station closed
O1.12 | -Blank docs folder-docs outdated;safety report form 2018,TCAS form 2018,old WFP OHR form with Presleys name on the form. -Folder labled 5Y-CGD CLEARENCES AND OTHER DOCS contains miscellaneous docs and no clearances | OMA | Minor | 2020-03-28 | 2020-06-01 |  |  | 2020-05-31 | CLOSED | None given | Partially closed.Station closed hence no full closur eof findings.
O1.08 | -DG Checklist not filled when rejecting DG Date 7.02.2020 EsMS report 39023 -Spill kit at the office as opposed to the aircraft.Retraining required on use of the DG spill kit. | DG Manual 10.08 | Minor | 2020-03-28 | 2020-06-01 |  |  | 2020-05-31 | CLOSED | None given | Partially closed,DG co-ordinator to discuss on directions to be given to personell during rejection of DG and use of spill kit
O2.04 | No procedure outlined in the SFOM on apologies or those absent | SFOM sec 6.6 | Minor | 2020-03-31 | 2020-06-01 |  |  | 2020-05-24 | CLOSED | None given | Station closed
O1.04 | Johns File had an index but missing most of the Content;SMS,First Aid,Indoctrination,CV,Passport copy,Flight and ground training. | OMA Sec 5 | Major | 2020-03-28 | 2020-05-04 |  |  | 2020-04-30 | CLOSED | None given | Closed Satisifactorily on time
O1.01 | ASL not displayed | KCARS 2018 | Minor | 2020-03-28 | 2020-06-01 |  |  | 2020-04-30 | CLOSED | Pictures of office board | Closed Satisifactorily on time
O5.04 | No evidence of Adam receiving brief from the PM between date of arrival 14.03.2020 and day of operation 16.03.2020 | SFOM Sec 11.0 | Major | 2020-03-31 | 2020-05-04 |  |  | 2020-04-30 | CLOSED | Handover signing form | Closed Satisifactorily on time
O1.07 | 11.01.2020 -Handover form Chepkwony not signed by incoming co pilot to show acceptance.No name of incoming co pilot | SFOM Sec 11.0 | Major | 2020-03-28 | 2020-05-04 |  |  | 2020-04-30 | CLOSED | Signed handover forms | Closed Satisifactorily on time
O1.02 | Auditee unfamiliar with company safety policy | SMS Manual Sec 1.3 | Minor | 2020-03-31 | 2020-06-01 |  |  | 2020-05-31 | CLOSED | Safety policy attached read and understood | Closed Satisifactorily on time
O1.06 | -Techlogs-Incoming Captain not indicating Licence number below signature.Techlog numbers 7509,7506,7510 -Nav Logs-14.03.20 30 min Fuel column not filled in as required -Nav Logs-10.03.20 old Navlog dated 2015 in use | OMA Sec 5 | Major | 2020-03-28 | 2020-05-04 |  |  | 2020-04-30 | CLOSED | Corrected navlog and Techlog extracts | Closed Satisifactorily on time
O8.01 | Kasas ERP at station contains both UNHAS AERP contacts 2018 and 25.05.2019 which can cause confusion in an emergency |  | Minor | 2020-03-31 | 2020-06-01 |  |  | 2020-05-31 | CLOSED | None given | Closed Satisifactorily on time
BAMAKO -MALI STATION
ITEM REF | NON CONFORMANCE | STANDARD USED | FINDING LEVEL | FINDING ISSUED ON | FIRST COMPLIANCE DATE | SECOND COMPLIANCE DATE | DAYS TO DUE DATE | AUDITEE CLOSURE DATE | FINDING STATUS | OBJECTIVE EVIDENCE | REMARKS | KEY
FLT 4.1 | At the time of the Audit ,Ambrose Simiyu First Aid Training expired on 30.03.2020. | SFOM sec 5.1;10.0 | Minor | 2020-06-04 | 2020-09-03 |  | 38 |  | OPEN
O1.07 | At the time of the audit there were missing signatures on Aircraft load sheets and operational flight plans | SFOM sec 4.3 OMA sec 8 | Minor | 2020-06-04 | 2020-09-03 |  | 38 |  | OPEN
Formulas:
DAYS TO DUE DATE = DAYS([FIRST COMPLIANCE DATE],TODAY())

## CONTRACTORS
| Last Updated: | 2020-07-27
ITEM REF | NON CONFORMANCE | STANDARD USED | FINDING LEVEL | FINDING ISSUED ON | FIRST COMPLIANCE DATE | SECOND COMPLIANCE DATE | DAYS TO DUE DATE | AUDITEE CLOSURE DATE | FINDING STATUS | OBJECTIVE EVIDENCE | REMARKS

## JAN-JUN ANALYSIS
Total Scheduled Audits | 22
Audits Done on time | 10
Audits Done late | 6
Audits not Done | 6
Total Findings raised | 33
Findings closed on time | 22
Findings closed late | 2
Ongoing closure | 2
Overdue for closure | 7
AUDIT PUNCTUALITY JAN-JUNE 2020
CLOSURE OF FINDINGS JAN-JUNE 2020